## Sheet1
City of Hollywood, Florida Department of Public Utilities – Engineering and Construction Services Division
Washington Park Phase 1
19-11042 (Drainage) 16-5136 (Water) 18-7089 (Sewer)
[6 empty] | DATE: | 2025-01-29
|  | NOTICE TO PROCEED |  |  | 2024-10-14 | DAYS |  | REMAINING
|  | COMMENCEMENT OF WORK |  |  | 2024-10-14
|  | SUBSTANTIAL COMPLETION |  |  | 2026-03-16 | 518 |  | 411
|  | FINAL COMPLETION |  |  | 2026-04-15 | 30 |  | 441
| [X ] | OWNER: |  | City of Hollywood |  | No. Copies |  | DAILY
| [X ] | ENGINEER: |  | Tetra Tech, Inc. |  | No. Copies |  | CONSTRUCTION
| [ ] | ARCHITECT: |  |  |  | No. Copies |  | REPORT
| [X ] | CONTRACTOR: |  | Man Con, Inc. |  | No. Copies |  | DAYS FROM
| [X ] | FIELD: |  | Tetra Tech, Inc., David Galeano |  | No. Copies |  | NOTICE TO
| [ ] | OTHER: |  |  |  | No. Copies |  | PROCEED
PROJECT DATA: | [5 empty] | CONTRACT DATA:
| NAME: |  | Washington Park Phase 1 |  |  | Tt NUMBER: |  | 200-16428-17001
| LOCATION: |  | Washington Park |  |  | DRAWING NO.:
| OWNER: |  | City of Hollywood |  |  | SPECIFICATION:
| CONTRACTOR: |  | Man Con, Inc.
1. | WEATHER |  |  |  | Temp. Range | Precipitation | 0%
| [ ] | Sunny | [ ] | Overcast | 60 | Type:
| [ ] | Cloudy | [ ] | Windy | 80 | Duration:
| [ X ] | Clear
2. | GROUND CONDITIONS |  |  |  |  | Time
| [ ] | Saturated | [ X ] | Dry |  | Observation Started: | 11:30
| [ ] | Frozen | [ ] | Wet but workable |  | Observation Stopped: | 15:00
3. | RECORD OF LABOR
Contractor |  | Type | No. | Hrs. (Each) | Contractor | Type | No. | Hrs.
Man Con Inc. |  | Foreman / Operator | 1
Man Con Inc. |  | Laborers | 3
Man Con Inc. |  | Foreman | 1
Man Con Inc. |  | Laborers | 3
4. | EQUIPMENT
Contractor |  |  | Type / Model |  | Qty. | Hrs. (Each) |  | Use Y/N
Man Con Inc. |  |  | Mini Excavator |  | 1 |  |  | Y
Man Con Inc. |  |  | Excavator |  | 1 |  |  | Y
Man Con Inc. |  |  | Ditcher |  | 1 |  |  | Y
Man Con Inc. |  |  | Pick up truck |  | 2 |  |  | Y
Received By |  |  | Qty-Ton | Type | Supplier | Use
5. | DESCRIPTION OF WORK PERFORMED
Time |  | Station | Sheet | Activity |  |  |  | Spec. Instruct.
6:15 - 7:15 |  |  |  | Crew working on drainage on Washington street near SR 7.
11:30 AM - 3:00 PM |  |  |  | There is one crew actively working on the installation of water services in the designated area of Dawson Street, located west of South 58th Avenue. This work typically involves: • Excavation: Crew digging trenches to access existing water mains to lay new water service lines. • Pipe Installation: New water service pipes are being connected to the water main and extended to individual properties or designated connection points. • Coordination: Crew is working on one side of the street at a time • Traffic Control and Safety: Temporary road closures are in place to ensure safety for workers and the public.
11:30 AM - 3:00 PM |  |  |  | Second crew installing sanitary sewer laterals on Funston street East of S 59 Avenue, work involves excavation, pipe installation, traffic control, and backfilling.
11:30 AM - 3:00 PM |  |  |  | Walked Funston Street to review drainage with Jeff Mancini and Hugo Davalos, only request was to relocate French Drain b/w CB 68 and CB 69 to the street, to avoide the gas line on the South side of the street.
6:15 - 7:15 |  | 12+00 - 21+00 | C-125, & C-128 | S 58th Avenue (Water) No water work at this time
6:15 - 7:15 |  | 26+50 - 30+00 | C-125, & C-128 | S 59th Avenue (Water) No water work at this time
6:15 - 7:15 |  | 802+00 - 827+00 | C-170 - C-172, C-176 - C-178 | Rodman Street (Sewer) No sewer work at this time
6:15 - 7:15 |  | 1101+00 - 1127+00 | C-173, C-182, C-183, C-189 - C-191 | Dewey Street (Sewer) No sewer work at this time
6:15 - 7:15 |  | 10+15 - 10+37 | C-173, C-185 - C-188 | Dawson Street (Sewer) No sewer work at this time
6:15 - 7:15 |  | 902+00 - 927+00 | C-172, C-174, C-175, C-179 - C-181 | Funston Street (Sewer) No sewer work at this time
6:15 - 7:15 |  | 12+00 - 21+00 | C-172, C-173 | S 58th Avenue (Sewer) No sewer work at this time
6:15 - 7:15 |  | 26+50 - 30+00 | C-184 | S 59th Avenue (Sewer) No sewer work at this time
6:15 - 7:15 |  | 25+00 - 38+00 | 7, 8, 9 | S 56th Avenue (Drainage) No Drainage work at this time
6:15 - 7:15 |  | 11+00 - 27+00 | 4, 20, 21, 22 | Rodman Street (Drainage) No Drainage work at this time
6:15 - 7:15 |  | 10+50 - 24+00 | 6, 14, 15 | Dewey Street (Drainage) No Drainage work at this time
6:15 - 7:15 |  | 11+00 - 37+00 | 6, 9 - 13 | Washington Street (Drainage) No Drainage work at this time
6:15 - 7:15 |  | 15+00 - 20+00 | 16 | Dawson Street (Drainage) No Drainage work at this time
6:15 - 7:15 |  | 12+00 - 28+00 | 5, 17-19 | Funston Street (Drainage) No Drainage work at this time
6:15 - 7:15 |  | 25+00 - 37+00 | 4, 5, 6 | S 58th Avenue (Drainage) No Drainage work at this time
6:15 - 7:15 |  | 30+00 - 34+00 | 14, 16 | S 59th Avenue (Drainage) No Drainage work at this time
END OF SECTION